| Excise Department of Sri Lanka |  |  |
| --- | --- | --- |
| Procurement Time Schedule |  |  |
| Procurement of Supply, Implementation, and Operation of a Security Features and Security Features Management System (SFSFMS) for Liquor-Based Products for Excise Department of Sri Lanka |  |  |
| Procurement Action | Days | Due Date |
| Approval of Procurement Document - By the Bid Evaluation Committee (BEC) and Procurement Committee (PC) |  | 16-Jul-26 |
| Publication of Invitation for Bids (IFB) - In a national newspaper and Websites | 4 | 20-Jul-26 |
| Issuance of Procurement Document - To prospective bidders | 1 | 21-Jul-26 |
| Pre-Bid Meeting - conducted to clarify requirements and address bidder queries | 14 | 4-Aug-26 |
| Deadline for Submission of Bids | 42 | 1-Sep-26 |
| Evaluation of Technical Bids - By the BEC | 21 | 22-Sep-26 |
| Approval of Bid Evaluation Report (BER) - By the PC | 7 | 29-Sep-26 |
| Notification of Qualified Bidders & Opening of Price Bids | 3 | 2-Oct-26 |
| Evaluation of Price Bids & Preparation of Combined Evaluation Report - By the BEC | 5 | 7-Oct-26 |
| Approval of Combined Evaluation Report - By the PC | 7 | 14-Oct-26 |
| Standstill Period (Appeal Period) | 14 | 28-Oct-26 |
| Cabinet Approval | 14 | 11-Nov-26 |
| Contract Award - To the successful bidder | 2 | 13-Nov-26 |
| Contract Signing - Formal execution of the agreement | 14 | 27-Nov-26 |
| Implementation Period - Commencement and execution of project activities | 180 | 26-May-27 |
| Support and Maintenance Period - Completion of warranty obligation | 1825 | 24-May-32 |
| Project Completion | 1 | 25-May-32 |